## Project Planner
The Comprehensive Nutritional Food Database Development
[5 empty] | Period Highlight | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
Activity No. and Name | Plan Start | Plan Duration | Actual Start | Actual Duration | Percent Complete | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
1.Intiating Phase | 1 | 30 | 1 | 0 | 0%
1.1 Define Project objective | 1 | 5 | 1 | 5 | 0%
1.2 Identify Project Stakeholders | 7 | 14 | 7 | 14 | 0%
1.3 Define Project Scope | 19 | 5 | 19 | 5 | 0%
1.4 Weekly Project Meetings | 4 | 1 | 4 | 1 | 0%
2. Planning Phase | 19 | 4 | 19 | 4 | 0%
2.1 Develop Work Breakdown Structure (WBS) | 23 | 5 | 23 | 5 | 0%
2.2 Estimate Activities and Resources | 28 | 5 | 28 | 5 | 0%
2.3 Create Gantt Chart | 33 | 4 | 33 | 4 | 0%
3.Execution Phase |  |  |  |  | 0%
3.1 Problem background | 37 | 8 | 37 | 8 | 0%
3.2 user requirements | 45 | 5 | 45 | 5 | 0%
3.3 Strutural design | 50 | 10 | 50 | 10 | 0%
3,4 documentations | 60 | 27 | 60 | 27 | 0%
3.5 deployment | 87 | 15 | 87 | 15 | 0%
0%
4,1 status report | 102 | 30 | 102 | 30 | 0%
4.2 Update plans | 132 | 15 | 132 | 15 | 0%
0%
5.1 Final performace review | 147 | 10 | 147 | 10 | 0%
5.2 Prepare Final Report | 157 | 5 | 157 | 5 | 0%
6.1 Frontend Development Tasks | 162 | 1 |  |  | 0%
7.Data management | 163 | 1 |  |  | 0%
7.1 Data Management Tasks | 163 | 1 |  |  | 0%
0%
8.Integration and Testing | 163 | 2 |  |  | 0%
8.1Integration and Testing Tasks | 165 | 2 |  |  | 0%
0%
9. Security Implementation | 167 | 2 |  |  | 0%
9.1 Security Tasks | 169 | 2 |  |  | 0%
10. Documentation | 171 | 2 |  |  | 0%
10.1 Documentation Tasks | 173 | 2 |  |  | 0%
11.Deployment | 175 | 1 |  |  | 0%
11.1 deployment Tasks | 175 | 1 |  |  | 0%
0%